## Start here
Pittsburgh Airport Terminal Record
Companion data to "Pittsburgh Airport cuts ribbon on $1.75 billion terminal"
Brian Nuckols, West Hills Gazette, Oct. 11, 2025.
The finding: a $1.7B terminal (budget up 54% / ~$600M), designed for 13-15M passengers
while 2024 demand was 9.95M, financed by ~$1.66B in airport revenue bonds whose $2.5B
lifetime debt service the Authority did not disclose at the ribbon-cutting but its audited
2024 financial report does.
Every figure traces to an archived, SHA-256-hashed source (see the Sources tab and
01-sources-archive/). Reproduce with: python 03-harness/check.py
Data is CC BY 4.0. Figures marked 'authority_claim' are the Authority's own numbers.

## Cost
date | label | budget_billions | delta_pct_from_prior | delta_millions_from_prior | source_id | note
2017-09 | Announced | 1.10 |  |  | story-published | Original budget when the terminal modernization was announced
2021-02 | First revision | 1.39 | 27 | 290 | story-published | Up 27% from the original
2023-10 | Second revision | 1.57 | 13 | 180 | story-published | Up another 13%
2025-04 | Final cost | 1.70 | 8 | 130 | story-published | Up another 8%. Ribbon-cutting headline figure rounded to $1.75B

## Passengers
year | passengers_millions | event | source_id
1999 | 20.0 | Peak hub era (~20M, late 1990s), US Airways hub | story-published
2002 | 15.1 | Still a major hub | story-published
2004 |  | US Airways de-hubbing (December 2004) | story-published
2013 | 7.8 | Post-de-hubbing low | story-published
2024 | 9.95 | Current demand | story-published

## Capacity
metric | value_millions | source_id | note
Designed capacity (low) | 13 | story-published | New terminal designed for 13-15M passengers/year
Designed capacity (high) | 15 | story-published | New terminal designed for 13-15M passengers/year
Current demand (2024) | 9.95 | story-published | Actual 2024 passengers

## Financing
source | amount_millions | type | disclosed | source_id | note
Federal (Infrastructure Investment and Jobs Act) | 129.7 | federal_grant | yes | story-published | Airport terminals program; $10.5M tranche corroborated via Deluzio release
State of Pennsylvania | 80 | state_grant | yes | story-published | State investment in the airport region
Series 2021 revenue bonds (2021A + 2021B) | 832.67 | revenue_bond | yes | acaa-acfr-2024 | Terminal Modernization Program; $719.85M AMT + $112.82M Non-AMT, issued Aug 26 2021
Series 2023 revenue bonds (2023A/B/C) | 415.03 | revenue_bond | yes | acaa-acfr-2024 | Terminal Modernization Program; 2023A $346.96M plus 2023B and 2023C, issued Oct 12 2023
April 2025 senior-lien revenue bonds | 410.5 | revenue_bond | yes | acaa-acfr-2024 | ~$410.5M issued April 2025; a subsequent event disclosed in the 2024 ACFR
BIOS state loan (PA DCED) | 6.0 | state_loan | yes | acaa-acfr-2024 | Business in Our Sites loan up to $7.8M; $450,940 drawn as of Dec 31 2024
2019 baseline (pre-project) | -70.9 | baseline | yes | acaa-cafr-2019 | By 2019 the Authority had defeased ~$70.9M and carried little long-term airport revenue debt; the terminal bonds came afterward

## Debt service
period | bond_principal_millions | bond_interest_millions | total_debt_service_millions | source_id | note
2025 | 0.00 | 64.60 | 65.18 | acaa-acfr-2024 | First year, interest-heavy (includes small BIOS-loan principal/interest)
2026 | 15.84 | 60.54 | 77.19 | acaa-acfr-2024
2027 | 20.44 | 59.74 | 80.99 | acaa-acfr-2024
2028 | 21.47 | 58.72 | 81.04 | acaa-acfr-2024
2029 | 22.55 | 57.65 | 81.04 | acaa-acfr-2024
2030-2034 | 130.87 | 274.10 | 409.58 | acaa-acfr-2024 | five-year bucket
2035-2039 | 166.53 | 239.01 | 408.04 | acaa-acfr-2024 | five-year bucket
2040-2044 | 208.10 | 197.84 | 406.31 | acaa-acfr-2024 | five-year bucket
2045-2049 | 261.37 | 146.30 | 407.67 | acaa-acfr-2024 | five-year bucket
2050-2054 | 305.87 | 74.76 | 380.62 | acaa-acfr-2024 | five-year bucket
2055-2056 | 94.67 | 12.88 | 107.55 | acaa-acfr-2024
Total | 1247.70 | 1246.13 | 2505.21 | acaa-acfr-2024 | Series 2021 + 2023 bonds, principal + interest to maturity (2056)

## Summary
metric | value | definition
cost_original_billions | 1.1 | Announced budget, Sept 2017
cost_final_billions | 1.7 | Final cost, April 2025
cost_escalation_pct | 54 | Percent over the original budget
cost_escalation_millions | 600 | Dollars over the original budget
demand_2024_millions | 9.95 | Actual 2024 passengers
design_capacity_millions | 13.0-15.0 | Designed annual capacity
utilization_pct_range | 66.3-76.5 | 2024 demand as a share of design capacity
excess_capacity_pct_range | 31-51 | Design capacity above current demand
financing_grants_millions | 209.7 | Federal + state grants (the disclosed public money)
modernization_bonds_outstanding_millions | 1247.7 | Series 2021 + 2023 revenue bonds, per the 2024 ACFR (the total the authority did not give at the ribbon-cutting)
all_terminal_bonds_incl_2025_millions | 1658.2 | Including the ~$410.5M issued April 2025
debt_service_to_maturity_millions | 2505.21 | Total principal + interest on the 2021 + 2023 bonds through 2056
annual_debt_service_near_term_millions | 77-81 | Roughly this per year in 2026-2029

## Sources
id | title | publisher | url | archived_path | supports
story-published | Pittsburgh Airport cuts ribbon on $1.75 billion terminal | West Hills Gazette | https://westhillsgazette.com/pittsburgh-airport-cuts-ribbon-on-1-75-billion-terminal/ | raw/story-published.html | The published story of record: cost-escalation sequence, capacity-vs-demand figures, financing, the authority's jobs/impact claims
acaa-cafr-2019 | Allegheny County Airport Authority — Comprehensive Annual Financial Report, year ended Dec. 31, 2019 | Allegheny County Airport Authority (audited, Plante & Moran) | https://flypittsburgh.com/wp-content/uploads/2020/04/Comprehensive_Annual_Financial_Report_For_the_Year_Ended_Dec._31_2019.pdf | raw/acaa-cafr-2019.pdf | Authority-level outstanding revenue bonds and annual debt service (audited). Scope note: covers all ACAA airport revenue debt, not the terminal project alone
acaa-acfr-2024 | Allegheny County Airport Authority — Annual Comprehensive Financial Report, year ended Dec. 31, 2024 | Allegheny County Airport Authority (audited) | https://flypittsburgh.com/wp-content/themes/Divi-ACAA/reports-financials/annual-comprehensive-financial-reports/Allegheny_County_Airport_Authority-2024_ACFR.pdf | raw/acaa-acfr-2024.pdf | Current (post-terminal-bond) outstanding revenue debt and annual debt service, audited. Authority-level scope (PIT + AGC)
acaa-economic-impact-study | Pittsburgh International Airport Economic Impact Study — Core Report | Allegheny County Airport Authority (commissioned) | https://flypittsburgh.com/wp-content/themes/Divi-ACAA/reports-financials/economic-impact/Economic-Impact-Study-Core-Report_Final.pdf | raw/acaa-economic-impact-study.pdf | The commissioned study behind the authority's jobs and economic-impact claims
acaa-reports-index | Reports & Financials | Allegheny County Airport Authority | https://flypittsburgh.com/acaa-corporate/newsroom/reports-financials/ | raw/acaa-reports-index.html | Index of ACAA annual financial reports; retrieval path for later-year CAFRs (2021-2024) that carry current debt service
faa-iija-terminals | Infrastructure Investment and Jobs Act — Airport Terminals Program | Federal Aviation Administration | https://www.faa.gov/iija/airport-terminals | raw/faa-iija-terminals.html | The federal Airport Terminals Program that funded part of the project ($5B nationally, $1B/yr 2022-2026)
deluzio-grant-2024 | Deluzio announces $10.5 million in federal funding for new Pittsburgh International Airport terminal | Office of Rep. Chris Deluzio | https://deluzio.house.gov/media/press-releases/deluzio-announces-105-million-federal-funding-new-pittsburgh-international | raw/deluzio-grant-2024.html | One documented federal grant tranche ($10.5M) toward the terminal; corroborates the federal-funding thread
cap-pit-terminal | Pittsburgh International Airport Terminal Modernization Program | Center for American Progress | https://www.americanprogress.org/article/pittsburgh-international-airport-terminal-modernization-program/ | raw/cap-pit-terminal.html | Independent write-up of the project scope, financing structure, and jobs claims (corroboration of the authority's figures)